Nimbus Electronics — Onboarding Plan

SOW-2026-002   |   Signed: 2026-02-02   |   Go-live: 2026-04-15   |   Hub: DFW

Scope

Warehousing + last-mile at the Dallas Fulfillment Center. Target OTD 97%. MRR $110,000.

Readiness gates

1) DFW capacity confirmed (see dfw_capacity_check_2026Q1) — currently TIGHT.

2) Staffing: 1 added shift lead required (see team_capacity_planner).

3) Delivery handoff owner: Nathan Osei (D03).

NOTE: 'start' 2026-02-02 refers to contract signing, not operational go-live (2026-04-15).